## Slide 1
Typical NC in Warm Modules
Following X-ray campaign
V. Baglin (21/8/12)
CERN TE-VSC, Geneva

## Slide 2
X-ray campaign
Started in January 2011 – to be finished at next TS
  1800 X-rays taken
  95NC (~ 5 %)
  58 vacuum sector concerned out of 190 at room temperature (88 sectors at cryogenic temperature)

## Slide 3
Example of documentation

## Slide 4
Reparation campaign
Started during winter technical stop 2011– 2012 :
  A5L1.B, A4L2.C, A4R2.C, IP5.X, A4L8.C, A4R8.C repaired
  Remains 52 vacuum sector
To be continued during LS1 :
  All vacuum sector to be open for activities other than VSC will be repaired
  Currently ~ 110 vacuum sectors are foreseen to be opened
  Remains 18 vacuum sectors not opened
  i.e 29 NC which need to be classified “use as is / repair “
    according to X-ray
    according to pressure activity in the vicinity
    according to impedance simulation
    according to impedance measurement

## Slide 5
Typical NC
Spring out
Deformation
Zero length overlap
Is this acceptable impedance wise ?

## Slide 6
Typical NC
Spring out
Deformation
Aperture restriction
  beam is passing trough since years
Is this acceptable impedance wise ?

## Slide 7
Typical NC
Spring out
RF fingers blocked
Overlap acceptable
Is this acceptable impedance wise ?

## Slide 8
Typical NC
Spring in place
1 RF finger out
Overlap acceptable
Is this acceptable impedance wise ?

## Slide 9
Typical NC
Spring in place
some RF fingers out
Overlap acceptable
Is this acceptable impedance wise ?

## Slide 10
Typical NC
Spring out
RF fingers blocked
Overlap acceptable
Is this acceptable impedance wise ?
Triggered a BD of fill 2978
Increase vacuum interlock => use as is for beam vacuum performances

## Slide 11
Conclusions
X ray campaign of warm module is (almost) finished !
95 NC disseminated in 58 vacuum sectors (30 % of total vacsec)
66 NC will be repaired (70 % of total NC)
29 NC are actually foreseen not to be repaired in 18 vacuum sectors
The repair of all NC would imply 15 % more activities in the tunnel => not acceptable
A sorting must be done by LRFF to:
  Propose the repair of critical VM
  Minimise the number of interventions